Project Planning

Reference Files

Table of Contents

Project Management Overview			Page 2

Case Study						Page 11

Project Purpose Statement			Page 13

Sample Project Charter				Page 16

Measurable Objectives				Page 18

Project Scope						Page 24

Project Assumptions					Page 30

Project Communications				Page 33

Project Deliverables				Page 40

Project Management Overview

Introduction:

A project is an organized activity with a well-defined purpose, completed by a dedicated project team within a given timeframe. In other words, a project has a beginning and an end; the end comes when you have achieved the project’s purpose.  Once you have achieved this purpose, the project is over.  The project team may stay together and work on extending the project’s purpose, but this is considered another project – for example the first project designs and implements a new self-service facility registration system for a recreation center (the project’s purpose) – improvements to this system after it has been released or the addition of a new function (such as the member changing how they pay their dues each month) which was not included in the first project are different projects, with a different purpose and different timeframes than the original project.

Triple Constraint:

As a project manager you will hear this term a lot.  It can be confusing because there are four constraints, not three.  These are cost, time, quality and scope.  Cost is  how much money you have to spend to complete the project; time is how much time you have to complete the project; quality is how According to Merriam-Webster Dictionary, a constraint is “the state of being checked, restricted, or compelled to avoid or perform some action”.  (see triple constraint for more details)

A Project is Accomplished Through a Series of Processes:

According to the Project Management Institute (www.PMI.org) a project is made up of five processes: project initiation, project planning, project execution, project controlling and project closing.  PMI has conducted a study showing that investing in project initiation and planning at the beginning of a project, before you incur most of the project cost, is the most effective way of ensuring that the project will meet its objectives. As the figure shows, a relatively modest investment at the start of a project will reduce by a much larger amount the cost of rework at later stages.  Also note that the return on investment from planning is not infinite.  As the cost of planning continues to increase at a steady rate, the cost of rework doesn’t continue to decrease at the same rate.

--

[Impact of Investing in Project Initiation and Planning]

--

A project plan is not a big investment of time or resources; it usually takes less than a couple of weeks to develop for most projects.  IT project managers often say that one day of planning saves 2-4 days of work during the project.  Who would turn down an investment opportunity with 100% to 300% return?

Project Initiation:

Projects can be initiated by anyone in an organization.  Regardless of who initiates a project, it is good practice to identify a project sponsor with enough authority and organization knowledge to do the following: make sure the planned outcome of the project will help the organization achieve its strategic objectives; assist in getting the right resources for the project (money, people, equipment); help get resolution to project issues in a timely manner (resource conflicts, disagreement on project objectives, changes to project scope, etc.); provide the project manager with the authority he or she needs to successfully complete the project.

Organizations do not have unlimited resources and invest in projects if they believe its outcome will add value to the organization.  Typically, value comes about when you solve a problem or exploit an opportunity, whether it is for competitive, economic or regulatory reasons. Projects are initiated as the direct result of opportunities or problems within an organization.  This is the project purpose.  Organizations define what business value means to them and how to measure it.  Business value can be categorized into several broad areas including, revenue/profit growth, cost reduction and capital utilization.  Examples might be improved customer retention, higher market share, lower cost of goods sold, etc.  In our project, the value is an increase in gym membership as a result of better facility utilization and the reduction in clerical cost as members self-register for facilities.

During the initiation process, the project manager works with management to develop the project charter, which includes: define the project purpose; how project success will be measured (see frame u: defining measurable objectives); project in and out of scope (see frame v: defining project scope); project manager authority (see frame w: project manager authority); and project deliverables (see frame x: project deliverables)  This process usually is a small percentage of the overall project time and cost and at the conclusion of this step, if it doesn’t appear a project will achieve the value expected, the project should be cancelled.  Otherwise the charter is used as input into the more detailed project planning process.

Project Planning Process:

The project charter is used as input into the planning process during which the following will be determined: what work will need to be done to achieve the project’s objectives (see frame a: work breakdown structure); how much time the project is expected to take; (see frame b: schedule development); how much the project is expected to cost (see frame c: cost estimating); what human resources will be needed to complete the project within the planned schedule and budget (see frame d: human resource planning); how will the project team communicate internally and with people and organizations that are going to be using the project’s output (e.g. gym members) (see frame e: communications planning); and how will the project team know if the project’s output meets the expectations of its users? (stakeholders such as gym members) (see frame f: quality assurance).

Just as with project initiation, if management believes that the project will not achieve its purpose within the time and cost budgeted, the project should be cancelled.  At this point in time very little resources have been consumed to create the project plan, certainly much less than will be if the project is continued.

Project Execution:

The ongoing management of a project is also critical to keep the project on track.  Project execution includes: acquiring the resources necessary to complete the project as defined in the project plan (people, money, equipment); providing any necessary training for the project team; reporting project status to all interested parties (stakeholders) throughout the project; and gathering and reviewing any changes that are requested by project stakeholders to determine whether the changes will be made or not (if a change is made, the project plan must be updated including at least one or more of the following cost, time, scope and quality).

Project Controlling:

Just as with project initiation and project planning, the project manager must be diligent in assessing whether the project is going to achieve its purpose or not within cost, time, scope and quality.  If not, the project manager must either identify what needs to be changed in order to correct this or should recommend the project be cancelled.  During the controlling process the project manager should identify experienced resources that can provide some of this oversight.  Their responsibility is to help the project manager monitor the project scope, schedule, cost and quality to assess whether the project is under control.  This is a continuous process that occurs throughout the project.  As problems are discovered, changes are identified that can be made to the project plan.  In the worst-case scenario, it is determined that the project cannot achieve its purpose within an acceptable time, cost, scope and quality and so it is cancelled.

Project Closing:

Project closing has traditionally not been considered very important. The project team and, indeed, management are eager to go on to new things.  However, organizations that take the time to analyze what happened on each project and learn from its successes and mistakes do better on later projects.  Project closing also includes some other very important activities: getting the client to accept the project with a formal signature; making or receiving any final payments; releasing the project resources; and organizing and storing the project files so they are accessible to others as needed in the future.

Closing the Project

When a project is done – the application is implemented, users know how to use it, and any missing documentation has been completed – the project team will most probably be disbanded. Part of the team may stay on to maintain the system, but others will go on to new areas. Before this happens, however, it is important to have a formal closing of the project.

This closing serves several purposes. First, this is the time to assess which of the measurable objectives have been accomplished and which require more time before they can be truly assessed. For the latter, you should create a benefits realization plan to follow up on them.

Second, you should make a list of requirements that were proposed but not implemented in the first release, as described in Chapter 11 in more detail.

Third, the entire project team should meet as a group and go over what happened on the project – what was done well and where the problems were. All the lessons learned on the project should be documented for use by future project teams as part of a continuous improvement effort.

Case Study

The case study revolves around a private gym called Bodies of Steel.  This gym has more than 2,000 members, with more than 60% of them being busy single, professionals who typically use the gym before and after work.  The gym provides a variety of products and services, including racquetball, basketball, swimming, pilates, weights, personal trainers and a full-service restaurant and bar.  Currently the gym is experiencing several major challenges, including: Members are complaining that it is difficult to make reservations because the front desk personnel are overworked and do not answer the phone quickly; and/or without seeing what is available the members have to ask the clerk many questions before finding a time that is suitable to them and available.  In addition, in this very competitive environment, the gym would also like to reduce the cost of their clerical personnel, in particular front-desk staff.  Even though the gym is facing these two difficult challenges, it continues to be successful because of the fun atmosphere where members can socialize with one another while getting in a workout or grabbing a meal and a drink.  The gym wants to make sure that this fun environment is not negatively affected by any changes to address the above opportunities.

Project Purpose Statement

Introduction:

The project purpose statement is often the first thing that someone interested in learning more about a project might read or hear from a project team member or another project stakeholder.  This purpose statement, like the proverbial elevator speech, should in a few words describe what the project is all about.  The purpose statement is part of the project charter that is created during the project initiation phase.  (See frame: project charter)

How is it created?

A project purpose statement is relatively short, typically just a few sentences.  This is what makes writing one hard, because these few sentences often must describe a project that is fairly complex.  In addition the audience reading it can be from different parts of the organization or possibly from outside the organization.

A great way to start writing a project purpose statement is by writing down the problems and/or opportunities the project is supposed to resolve.  When writing these make sure you demonstrate how the problems/opportunities affect the business.

For our gym example, it is not enough to say, “This system will improve customer service and reduce payroll costs.”  Instead you should describe the problems and opportunities addressed by the project along the following lines:

“Our facility is overcrowded at some times, when several people who have been unable to make reservations show up at the same time, and underutilized at other times, when people who might have come haven’t been able to get through to make reservations.

Our front-desk employees spend an average of three hours a day taking telephone reservations, mostly at mealtimes and just before closing. As a result, the employees work longer hours than scheduled (and are paid for overtime) and are not productive at their other tasks. We therefore have an opportunity to reduce personnel costs while getting more work done and improving client satisfaction.”

Project Purpose Statement

Once you have described the problems and opportunities you can articulate the project purpose.  In our example, the project purpose is the following:

“The purpose of this project is to provide customers with self-service registration for athletic facilities to improve customer access, reduce clerical personnel cost and improve facility utilization.”

You must be very careful to state the purpose in business terms. The statement should be short, yet clearly understood by management and other stakeholders.  It is best to use the stakeholders’ own words to describe the problems and opportunities and how your project will address them.

What it isn’t:

You should avoid using technical terminology, as in the following sample purpose statement:

“The gym’s server must be upgraded from a Dell Dimension XPS R450 to a Sun Microsystems E450 w/2 Gig RAM, 2 X 400Mhz Processors, 4MM Tape Unit(X6261A), CD ROM, 4 X 18Gb Drives, PGX Video and Country Kit.  This upgrade will enable Bodies of Steel to implement web based facility registration.”

While this statement would be very understandable to the IT department and possibly to your project team, most of the information in it would be irrelevant to other stakeholders: management, clerical personnel and customers.

How do you know when you are done?

A great way to test your project purpose statement is to try it out on a few people not on the project team.  Share your project purpose and ask the person you are testing it on to describe the project to you in more detail.  If a few different people can do this to your satisfaction, you have written a great project purpose statement.

Sample Project Charter

Draft Project Charter – February 23, 2XXX – Version 1.0

(Created by the project manager with stakeholder input and management sign-off)

Project Purpose: This project is meant to provide customers with self-service registration for athletic facilities to improve customer access, reduce clerical personnel cost and improve facility utilization.

Prioritized Measurable Objectives: Provide a way for customers to self-register for center facilities. Expand the hours where customers can make reservations to 24 hours per day, 7 days per week. Implement the new registration system by October 1, 2XXX, in time for the busy fall season. Reduce clerical costs by 20% per year. Improve center utilization to 65% during off-peak times (off-peak is Monday to Friday between 9 AM and 4 PM and all day Saturday and Sundays).

Project Manager Authority: In order for this project to be successful, the project manager will need the authority to: Determine the project approach, including milestones; deliverables; and schedule. Determine project resource requirements, including funding, people and equipment. Determine how to allocate/reallocate project resources throughout the project. Fire project team members. Identify and communicate directly with all project stakeholders as the project manager sees fit. Determine which recommendations to implement if the project sponsor/project stakeholders do not provide this feedback within three business days of it being requested. The project manager does not have the authority to do the following without first getting the project sponsor’s approval: Cancel the project. Increase project funding beyond what is approved in the project plan. Extend the overall project timeframe beyond six months.

Project In-Scope: Increase non-peak center utilization Decrease clerical costs Positively impacting the fun atmosphere Promote the new system with members Address basketball, racquetball, weight stations, swim lanes, pilates and personal trainers

Project Out-of-Scope: Increase peak utilization Increasing the size of the gym Adding new products and services Increasing membership Reassign clerical staff Fire clerical staff Assist clerical staff with new employment Free weights, open swim, restaurant and bar

Project Assumptions: Utilization analysis will be conducted for five different days/times for each product/service offering in scope at the beginning of the project and then again for the same days/times at the conclusion of the project. This will be done three different times at the beginning and at the end of the project. An average of these wait times will be used for comparison purposes. These days/times and locations will be determined by the project team. Front-desk clerks adversely affected by the project changes will get assistance with either finding a new job within the gym or if they choose with another organization. Currently we expect that 15% of our clerical staff will be impacted by this change. This will be clearly communicated to the staff affected at the beginning of the project by the project sponsor. A bonus of $500 will be paid to front-end clerks who continue with the gym until the self-registration system is being used by more than 50% of our members.

Deliverables: Analysis of current facility utilization during off-peak times Analysis of clerical costs pre-implementation Recommendations for increasing off-peak utilization Self-service registration system requirements Self-service system technology selection Working self-service system Promotional materials/incentives to generate system usage System training materials and training Analysis of clerical costs post system implementation Analysis of post-implementation facility utilization during off-peak times

Approved by:

Project Sponsor: 	 		Date: February 26, 2XXX

--

Measurable Objectives

Introduction:

A good way for an organization to know if a project has been successful is by painting a picture of what the project will produce at its conclusion.  “If you don’t have a clear destination in mind, any old path will do.” (Source unknown) Defining measurable objectives is a great way to paint a picture of the project’s destination.  These objectives are part of the project charter (see project charter frame) and are listed right after the project purpose.

You may have thought that the purpose statement will do this for your project; although it provides important information regarding the project’s purpose, it does not provide a way to measure if you have accomplished your purpose at the end of the project.  The only way the organization will know if the project has been completed successfully is if you have established measurable objectives up front, which define how well you have solved the problem or seized the opportunity that made you undertake the project in the first place. As Peter Drucker puts it, “What gets measured gets done.”  By describing the purpose and objectives in business terms, you make clear what the stakeholders can and cannot expect of the project.

How are Measurable Objectives Created?

Developing measurable objectives which link your project objectives to the overall business problems and/or opportunities is critical to making sure your project gets the resources it needs to be successful.  Otherwise management probably won’t understand the value your project is providing to the organization and other projects may get their attention.

Remember what our organization’s problems are from the case:  “Our facility is overcrowded at some times, when members who have been unable to make reservations show up at the same time, and underutilized at other times, when people who might have come haven’t been able to get through to make reservations;” and “our front-desk employees spend an average of three hours a day taking telephone reservations, mostly at mealtimes and just before closing. As a result, the employees work longer hours than scheduled (and are paid for overtime) and are not productive at their other tasks. We therefore have an opportunity to reduce personnel costs while getting more work done and improving client satisfaction.”

From this we wrote our project purpose statement: “The purpose of this project is to provide customers with self-service registration for athletic facilities to improve customer access, reduce clerical personnel cost and improve facility utilization.”

Using this information as the starting point, we can write measurable objectives for our project.  Keys to writing good measurable objectives include: objectives can be accomplished by the team within the timeframe allocated; when accomplished the project team can measure that the objective has been completed; objectives are clear enough that the project team understands what they must do to accomplish the objectives.  Measurable objectives for the University Athletics system might be:

- Provide a way for customers to self-register for center facilities.

- Reduce clerical costs by 20% per year.

- Expand the hours where customers can make reservations to 24 hours per day, 7 days per week.

- Improve center utilization to 65% during off-peak times (off-peak is Monday to Friday between 9 AM and 4 PM and all day Saturday and Sundays).

- Implement the new registration system by October 1, 20XX, in time for the busy fall season.

Each of the above objectives is measurable.  At the conclusion of the project, you can easily determine (measure) if you have accomplished them or not.  At the same time these objectives provide enough information for the project team to use to make decisions about how to implement the new self-service registration system.  For example, the project team knows they must implement a system that allows customers to self-register, and that they have to do this by October 1st.  Based on these objectives, the team can quickly start to narrow in on solutions that meet these requirements and eliminate others that do not.

You should also work with management to prioritize these objectives so that the most important are given the most attention throughout the process.   For instance if center utilization is more important than reducing clerical costs, the team may spend more time on improving utilization than on finding ways to reduce clerical costs.  If reducing clerical costs is more important, the team may find that sacrificing a few percentage points of utilization helps them achieve the cost savings.  The project team will be faced with many decisions throughout the project; these prioritized objectives will help them make better decisions in a timely manner.

Prioritized Measurable Objectives:

Provide a way for customers to self-register for center facilities.

Expand the hours where customers can make reservations to 24 hours per day, 7 days per week.

Implement the new registration system by October 1, 2XXX, in time for the busy fall season.

Reduce clerical costs by 20% per year.

Improve center utilization to 65% during off-peak times (off-peak is Monday to Friday between 9 AM and 4 PM and all day Saturday and Sundays).

To be convincing when you measure the project results at the end, it is important to have collected this same data at the start of the project for comparison purposes. In the example of University Athletics, the team spent some time up front actually measuring things like the time spent on hold, wait times, actual facility utilization, and so on. You should then ask management and other stakeholders to sign off on these figures, which represent the “as-is” state and can serve as a basis for comparison at the end of the project.

What Measurable Objectives are not!

Measurable objectives are still specified at a fairly high level and have to be further defined into a set of project specifications or requirements.  For example it is clear that a new system must be created where customers can self-register, but it is not clear from this information the form that this system will take.  Self-registration could be handled by a third-party, done over the telephone or by using a web based system among other potential solutions.  These details will be determined during the project planning phase.  (See project deliverables for more information)

How do you know when you are done?

Review your objectives against your project purpose and the business problems and/or opportunities.  It should be clear that once these objectives are met, the project purpose and business problems/opportunities are also met.  If this is not the case, you need to continue to either identify additional objectives or modify these objectives to address these needs.

These objectives are included in the project charter.  (see project charter)  Now you can start to identify project scope.  (see project scope)

Project Scope

Introduction:

Project scope is created during the initiation phase and is part of the project charter (see project charter frame). The project scope is simply what must be done (in-scope) and what will not be done (out-of-scope) to accomplish the project objectives.  Since you have already defined these objectives in measurable terms (see measurable objectives frame), it should be relatively straightforward to identify what is included in the scope (in-scope) and what isn’t (out-of-scope).

In-scope is anything we will have to perform to address the problem or opportunity we are working on during the project.  Out-of-scope is anything that is either not related to what we are working on or which is related, but not necessary to complete to achieve our project objectives.  Although it would be nice to be able to work on every aspect of the project, this is not realistic.  All projects have limited time and resources (money, people, and equipment) in which they must be completed.  By limiting our scope, we can make sure to focus on those things that must be done to achieve our project objectives in a reasonable period of time for a reasonable amount of resources.  These out-of-scope items can be reassessed and done during future projects if it makes sense to do so.

How is it created?

In order to begin determining what is in and out-of-scope, make a list of everything that you think must be done to achieve the project’s objectives.

Our project objectives as of February 23rd, 2XXX:

- Provide a way for customers to self-register for center facilities.

- Expand the hours where customers can make reservations to 24 hours per day, 7 days per week.

- Implement the new registration system by October 1, 2XXX, in time for the busy fall season.

- Reduce clerical costs by 20% per year.

- Improve center utilization to 65% during off-peak times (off-peak is Monday to Friday between 9 AM and 4 PM and all day Saturday and Sundays).

Based upon these objectives, we brainstorm with our team in order to compile a list of things to be completed in order to achieve them.

Our list for our case:

- Design a self-registration system for services that require reservations (this is the most realistic option for a 24/7 registration system where we are trying to save money on front-desk staff)

- Determine how members utilize services that typically do not require reservations such as open-swim, free weights and the restaurant/bar

- Identify self-registration system solutions used by other gyms or membership organizations

- Pick a self-registration system to use

- Identify new products and services which will attract members to use our facility during off-peak times

- Develop and install the new system

- Test the new system

- Train users on the new system

- Increase membership

- Add new functions based on user feedback

- Promote the new self-registration system with members

- Survey existing center utilization during off-peak times (9 am to 5 pm on Monday to Friday and on weekends)

- Reassign/fire clerical staff

- Identify ways to increase utilization during off-peak times

- Increase the size of the gym

Now review this list to determine which of these items must be done to achieve our objectives and which ones can be put aside or done by other project teams.  Clearly we must select and implement the new self-registration system, train users on the system and promote its use with our members.  We also must survey member utilization during off-peak times and identify ways to increase utilization during these times in order to achieve our objective “improve center utilization to 65% during off-peak times.”

At the same time increasing membership may seem like something we must do to complete this project, but it is of such a large scope in and of itself, we have decided to leave this out-of-scope of our project with management’s approval.  By leaving this out, we can still achieve our project’s objectives.  In addition, by leaving it out as we brainstorm ways to improve center utilization, the team will know not to include any items that would require adding new members (or at least note ideas for future projects).  So after brainstorming with our project team and reviewing this with management, we have identified the following for project scope.

Project In-Scope:

- Increase non-peak center utilization

- Decrease clerical costs

- Positively impacting the fun atmosphere

- Promote the new system with members

- Address basketball, racquetball, weight stations, swim lanes, pilates and personal trainers

Project Out-of-Scope:

- Increase peak center utilization

- Increase the size of the gym

- Add new products and services

- Increase membership

- Reassign clerical staff

- Fire clerical staff

- Assist clerical staff with new employment

- Free weights, open swim, restaurant and bar

As a project progresses, the scope may need to change. The team may discover unforeseen difficulties as they get more and more into the details.  The team may also discover that some objectives cannot be met without compromising the budget or the deadline. Finally, external conditions may change: the competition or the regulatory environment may change management’s priorities.  Management may then decide to change the objectives (and therefore the scope) of the project.  After having set the initial scope, the project manager must therefore be prepared to maintain it over time, continually keeping the team and other stakeholders informed of any changes.  Since scope is defined in the project charter and the charter is approved by management, the project manager must get approval from management for any changes in project scope.

Changes to scope are not necessarily bad if they improve the projects chances of success as defined in the project charter.  They are bad if you are adding additional requirements and/or improving product quality that was not defined in your project charter (This is commonly referred to as gold-plating).  If you are constantly changing the project scope, you will never finish the project.  As the project manager you must be make sure that you and your team can spot any changes to scope and assess their impact on the project cost, schedule and quality prior to requesting the change be approved by management (see triple constraint).

One of the biggest problems projects face is commonly referred to as scope creep, when the scope gradually increases over the course of the project.  This usually occurs when users and team members get overenthusiastic about what the system can do – “If we just add one or two simple items to the scope…” – and keep adding little items one at a time, until the project timetable and budget must be revised.  These changes are not necessary to achieve our project objectives.  By clearly defining measurable objectives and project scope up front, making sure your project team and project stakeholders understand scope and monitoring it continuously throughout the project, you can reduce the chances of scope creep happening to your project.  For our project, the new self-reservation system can always be improved upon, and the same is true for clerical efficiency and center utilization.  Your focus must be on achieving the projects objectives which include schedule and budget constraints.  In order to do this, you must not allow scope creep.  A better way to handle this is by noting these “improvements” and dealing with them on future projects.

What it isn’t:

It is easy to confuse scope with objectives.  Although it is related, it is also different in a very important way.  Scope is different than objectives because it differentiates between work that you will and will not do to achieve these objectives.  This is not made clear in project objectives, so scope helps you further clarify what work you will do to achieve them.  This is critical to your project if you want to complete it within time and budget!

How do you know when you are done?

With scope you are never done!  You must diligently watch to make sure that only work which is in-scope is being done throughout the project.  At the same time as project team members and other stakeholders approach you with work that is out-of-scope, you must assess whether this will require a scope change.  Avoid this whenever possible and push for this work to be done in another project.  This is one of your most important jobs as project manager!

Project Assumptions

Introduction:

According to the Merriam-Webster dictionary an assumption is: “to take as granted or true.”  We all make assumptions every day; unless we confirm these assumptions with whomever we are working, these may in fact be false and could have a significant negative impact on our project success.  What makes assumptions difficult to identify is that they are largely made at the unconscious level; they define who we are and how we think often based on our cultural background.  When you bring different people together to work on a project, they typically come from different backgrounds (cultures) and therefore make different assumptions.  These assumptions must be made explicit so that the project team and other stakeholders have a clear understanding of one another and of the project.

How are Assumptions Identified?

Let’s start with our project.  As we define the elements in our project charter, we must ask ourselves what must happen for this element to be true.  One of our objectives explicitly stated that we will reduce clerical costs by 20%.  For this to be true a number of things must happen.  This includes a new system that members can use to register must be accessible to and used by our members.  These things are explicitly stated in our charter.  At the same time for this to be true, we can’t lose all of our clerical staff during the transition to the new system.  If we do, we will have to hire and retrain new staff along with dealing with other disruptions to customer service.  This will cost us money, distract us from our project and create customer service problems during the transition to the new system.  Of course this makes perfect sense and everyone on the project team was aware of this, even though it wasn’t explicitly stated; maybe or maybe not.

Either way, this assumption must be stated explicitly so we can manage it during the project.  Our assumption is as follows and noted in our charter:

“Front-desk clerks adversely affected by the project changes will get assistance with either finding a new job within the gym or if they choose with another organization.  Currently we expect that 15% of our clerical staff will be impacted by this change.  This will be clearly communicated to the staff affected at the beginning of the project by the project sponsor.  A bonus of $500 will be paid to front-end clerks who continue with the gym until the self-registration system is being used by more than 50% of our members.”

What Assumptions are not!

Project assumptions are not the objectives, deliverables or requirements.  Assumptions simply help clarify for our project team and stakeholders what we mean when writing these objectives and other elements of our project plan.

How do you know when you are done?

Most of the assumptions you will identify will be during the project planning phase as you are defining the project.  A great way to confirm that the project team and your stakeholders understand the plan (and therefore all critical assumptions have been made explicit) is by having them tell you in their own words what the project outcome will be.  This will be a back and forth discussion during which either additional assumptions will surface or no additional assumptions will be identified.  You will need to do this with all project team members and key stakeholders.  We have found that doing this as a group both saves time and creates an environment more conducive to identifying implicit assumptions.

Project Communications

Introduction:

According to the Merriam-Webster dictionary communication is: “a process by which information is exchanged between individuals through a common system of symbols, signs, or behavior.” We all communicate every day both verbally and non-verbally.  In fact ineffective communications is one of the top reasons projects get into trouble.  A key to your success as a project manager is knowing whom you need to communicate with, in what form and how often.  This information is the basis of your communications plan.

How Do You Communicate on a Project?

Communications can take many forms both formal and informal.  Formal communications include project kick-off meeting, status reports, roles and responsibilities matrix, presentations, project deliverables, change requests, etc.  Informal communications are just as important, if not more important and typically occur more often.  These might include dropping in on a project team member to see how things are going, a chance meeting in the hall with a project stakeholder who asks for a quick project update, etc.  A key to effective communications in these situations is to do more listening than talking.  Since communications includes both verbal and non-verbal elements (non-verbal makes up more than 50% of the communications signal), e-mail is not a very effective tool to use for communicating.  Whenever possible it is better to meet face-to-face with the people you are communicating with.  If this is not possible, or practical, meeting over the phone is better than via e-mail.

Communicating regularly with your project stakeholders is one of if not the most important things you can do as a project manager.  It keeps you in touch with your team, it helps you surface issues earlier than if you wait until the regularly scheduled status meetings, and if you also use informal communications methods you often learn things that you might not have using formal channels.

There are many tools you can use to manage project communications; the two that I have found to be the most effective and easiest to use are the stakeholder’s analysis and a roles and responsibilities matrix.  A stakeholder’s analysis includes information about who we are communicating with, what needs to be communicated and how often.

Stakeholder Analysis

One of the first things a project sponsor and/or manager must do is a stakeholder analysis.  These individuals will provide important information during the development stage and throughout the project.  A stakeholder is anyone who will be affected by the project.  It is important to conduct a stakeholder analysis to identify these individuals or groups including their name, organization, role on the project, level of interest, level of influence, unique facts, expectations (how they define success) and ways to manage their expectations.  This information is important because it is these individuals who will identify the system requirements and provide project resources and support.  If the team misses an important stakeholder or doesn’t manage the stakeholders’ expectations, these individuals could work against the project and keep it from achieving its objectives.

Stakeholder information is collected by interviewing the stakeholders.  It may be sensitive and should be tightly controlled.  At the same time it is vital so that the project team can understand and manage these key stakeholders expectations.

An example stakeholder analysis follows:

| Name | Organization | Role | Interest | Influence | Unique Facts | Expectations (success means) | Ways to Manage Expectations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Jim | Chief Operations Officer for Bodies of Steel | Project Sponsor | High | High | Very demanding likes to know the details. Expects to get this information verbally. | Jim sold this to management and his job is at stake if the project isn’t successful. He expects the project will reduce payroll costs by 20% for customer service employees. | Currently Jim’s objective of a 20% reduction in payroll costs for clerical staff is considered aggressive. Meet with Jim as soon as possible to discuss this and agree on how to best approach achieving this or making adjustments to it. |
| Sue | Chief Executive Officer | Steering Committee | Medium | High | Not interested in details, just results and how this affects the bottom line | Not convinced this is a good investment, but is willing to let Jim take this risk. Of course if it doesn’t work, Jim may lose his job. She expects that the project will reduce costs, but also significantly hurt customer relationships and loyalty. | Make sure that the project objectives are clearly tied to improving customer relations. Get a quick win or two, which shows how customer relations will be improved by the new system. Show how the project team will also manage project costs and provide a good return on investment. |
| Clerical Staff | Customer Support | System Users | High | Low | Customer Support is mostly made up of people who have been around for a long time and have poor computer skills | Most of these people are very afraid of the new system. They think they may lose their jobs because the new system will replace them. | Get this group involved early in identifying system requirements while helping them to understand the project purpose and their role in the project. Make sure they receive sufficient training and are involved in all aspects of the project. |
| Customers | N/A | System Users | High | Medium | In general your customers are very sophisticated. Many are professionals with very little spare time. They want things to be easy and fast. They also expect things to work on the first try. | The customers aware of the new system are excited. They hate the current process and expect the new system will let them register for available facilities at their leisure. They also expect that like with the current system, the old timers will continue to get their court preferences. | Based on the customer’s feedback, there are some incorrect expectations. When the registration process is automated it will be first come first serve and customers will not always get their court preferences merely the time and type of facility if they are available. It will be important to regularly communicate with stakeholders and hold several open houses to discuss project plans. |
| Don IT Manager | Information Technology | Steering Committee | Low | Low | Don is busy with several other initiatives that he believes are higher priority. | He is unfamiliar with the new technology being implemented but has heard from his friends at other companies that it doesn’t work. He expects that he will have to save the customer service folks again on this project. | Get Don involved early. Try to demonstrate why this project is so important to the company. Get some quick technology wins to build his confidence in the new system and the project team. |
| Mary | Customer Support | Process Owner | Medium | Medium | Mary designed the current process and forms. She doesn’t see the need to change it and is afraid she may lose her power as a result of this project. | She doesn’t know what to expect and is unclear about her role on the project team. | Get with Mary as soon as possible to discuss and address her concerns. Make sure she is clear about her role on the project team. |
| HR | Human Resources | Steering Committee and Human Resource Allocation | Low | Low | HR is too busy with many other more important initiatives | Unclear | Schedule a meeting with the head of HR to discuss the project and find out more about their needs and expectations. |

It is common for the project manager(s) to schedule face-to-face meetings with key stakeholders at the beginning of the project.  One of the most important things to get from these meetings is how the stakeholder defines project success (their expectations).  This information can then be used to refine the project purpose and objectives.  If for some reason the stakeholders’ expectations are different than those of the project team, this is an opportunity to communicate this and begin to manage these expectations.  These will also need to be managed throughout the project, as stakeholder expectations often change over time.  By including key stakeholders in regular status meetings and sending this type of information to other stakeholders as part of the project communications plan, the project manager can better manage these changing expectations.

Decision Making

A key to project success is having a defined timeframe in which decisions are made by management.  It is common to require all project decisions be made within three business days of being presented to management.  This is referred to as decision time boxing.  If management doesn’t decide within three business days, the team goes ahead with the recommended solution.  In addition to time boxing, management should make sure the project team is clear about which decisions they can make on their own and which ones would require consulting management.

A simple table can be used to clarify this for the team:

| Team empowered to make decision | Team must consult management |
| --- | --- |
| No change to project time or resource estimates | Change will require additional time and/or resources |
| No change to project objectives and/or measures | Change to project objectives, and/or measures |
| Change only effects processes, technology or departments within scope | Change will effect processes, technology and/or departments outside project scope |

The project team discovered that current athletic facility usage is not being captured on a regular basis.  For the project to be able to achieve its objectives, this information must be collected.  Either the project team would have to develop a way to collect this information or the department responsible for this will need to start doing it more regularly.

The team realized they need to get management approval to collect this data since capturing facility usage would require additional time and resources to accomplish.  Until this is decided no further work can be done on this part of the project.  Fortunately the team had already agreed with management how the team would make these decisions and who was empowered to make them.  Based on this agreement, the team pulled together a presentation showing three different ways to solve this problem, including the pros and cons of each scenario and the team’s recommendation.  These were immediately sent to the decision makers via e-mail.  A meeting was also requested at which time a decision would be made.

What a Communications Plan is not!

A communications plan is just that, a plan.  It is not a substitute for getting out and talking to your stakeholders and project team members on a regular basis.  You may remember the old saying written about by Tom Peters called “Manage by walking around.”  This is just as relevant today as it was back then; your communications plan simply supports you while you are out meeting with your team and project stakeholders.

How do you know when you are done?

You are done with communications at the end of the project and never before!  This is an on-going process during which you will regularly communicate with your project stakeholders and team members.  On any project things are constantly evolving, you must keep yourself, your project stakeholders and team informed of these changes in a timely manner for your project to have a better chance of achieving its objectives.

Project Deliverables

Introduction:

A deliverable is the output of a project.  These are the things that you must create and deliver to your project stakeholders in order to achieve your project purpose and objectives.

How are Deliverables Identified?

Start with the project’s purpose, objectives and scope, use this information to identify what you will need to produce for your stakeholders in order to complete the project.  Some of these deliverables will be very similar to your project objectives.  For instance one of our deliverables for our project will be creating a system that members can use to make reservations for our facilities.  Others will not be so obvious but absolutely necessary for the project to be successful.  An example might be promoting the new system with members so they will use it.  Remember what Steven Covey said “Begin with the end in mind.”  Deliverables help you and your stakeholders visualize the end of the project.

After reviewing the project purpose, objectives and scope, the project team developed a list of project deliverables as follows:

- Analysis of current facility utilization during off-peak times

- Analysis of clerical costs pre-implementation

- Recommendations for increasing off-peak utilization

- Self-service registration system requirements

- Self-service system technology selection

- Working self-service system

- Promotional materials/incentives to generate system usage

- System training materials and training

- Analysis of clerical costs post system implementation

- Analysis of post-implementation facility utilization during off-peak times

What Project Deliverables are not!

Project deliverables are not a list of detailed work that has to be done to complete the project.  You will use these deliverables to develop that list when you create your project work breakdown structure.  (See work breakdown structure)

How do you know when you are done?

The way you will know when you have completed your project is when your stakeholders tell you that you have delivered on your promises.  They will do this by reviewing your deliverables and providing you with their signature of acceptance.  This occurs throughout the project not just at its completion.  Note that many of the deliverables are completed and delivered to the stakeholders during the course of the project.  An example is the self-service registration system requirements.  By developing these and getting approval as early as possible in the project, we reduce our risk of producing a system that does not meet our stakeholder’s needs.

# Text boxes

Cost

Cost of Initiation and Planning

Cost of Future Rework

Time

James Marlatt